## Exhibit A - Proposal Form
RFP 37-2025 - West Boundary Road Construction (Big Cypress) (No. 384023) Exhibit A - Proposal Form REV001
The work to be performed under this Contract shall consist of furnishing all personnel, tools, equipment, materials, supplies, and manufactured articles for furnishing all transportation and services, including fuel, power water and essential communications, and for the performance of all labor, work, or other operations required for the fulfillment of the Contract in strict accordance with the Contract Documents.
Item No. | FDOT Pay Item | Unit | Est. Qty. | Description | Unit Price | Total Cost
ROADWAY
1 | 102 1 | LS | 1 | MAINTENANCE OF TRAFFIC |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
2 | 102 2 | LS | 1 | MOBILIZATION/DEMOBILIZATION - including but not limited to all labor and materials required as well as all bonds, fees and insurance, the aggregate sum amount of: |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
3 | 104 10 3 | LF | 39300 | SEDIMENT BARRIER |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
4 | 104 11 | LF | 450 | FLOATING TURBIDITY BARRIER (at Cowbone Culvert Crossing) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
5 | 104 18 | EA | 21 | INLET PROTECTION SYSTEM |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
6 | 110 1 1 | AC | 29.7 | CLEARING & GRUBBING (based on right of way width) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
7 | 110 4 10 | SY | 144 | REMOVAL OF EXISTING CONCRETE (at Cowbone Culvert Crossing) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
8 | 120 1 | CY | 20401 | REGULAR EXCAVATION |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
9 | 120 5 | CY | 100 | CHANNEL EXCAVATION (at Cowbone Culvert Crossing) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
10 | 120 6 | CY | 7302 | EMBANKMENT |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
11 | 125 3 | CY | 50 | SELECT BEDDING MATERIAL (at Cowbone Culvert Crossing) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
12 | 160 4 | SY | 68529 | TYPE "B" STABILIZATION |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
13 | 285 701 | SY | 40417 | OPTIONAL BASE, BASE GROUP 01 (PATH & SHOULDER WIDENING) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
14 | 285 706 | SY | 10088 | OPTIONAL BASE, BASE GROUP 06 (3-LN & TURN LANE WIDENING) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
15 | 286 1 | SY | 2722 | TURNOUT CONSTRUCTION/DRIVEWAY BASE- OPTIONAL MATERIALS |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
16 | 286 2 | TN | 225 | TURNOUT CONST, ASPHALT/DRIVEWAY BASE- ASPHALT MATERIAL (1.5") |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
17 | 327 70 4 | SY | 48484 | MILLING EXISTING ASPHALT PAVEMENT, 3.0" AVG DEPTH |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
18 | 334 1 53 | TN | 4880 | SUPERPAVE SP-12.5 ASPHALTIC CONCRETE, TRAFFIC C, PG76-22 (1.5") |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
19 | 337 7 82 | TN | 7805 | ASPHALT CONC FRICTION COURSE, TRAFFIC C, FC-9.5, PG 76-22 (1.5") |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
20 | 425 1549 | EA | 18 | INLETS, DT BOT, TYPE C |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
21 | 425 1589 | EA | 1 | INLETS, DT BOT, TYPE H, MODIFY |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
22 | 430 175 118 | LF | 1550 | PIPE CULVERT, OPTIONAL MATERIAL, ROUND, 18" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
23 | 430 175 124 | LF | 610 | PIPE CULVERT, OPTIONAL MATERIAL, ROUND, 24"S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
24 | 430 175 218 | LF | 2862 | PIPE CULVERT, OPTIONAL MATERIAL, ELLIP/ARCH, 14"x23" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
25 | 430 175 224 | LF | 285 | PIPE CULVERT, OPTIONAL MATERIAL, ELLIP/ARCH, 19"x30" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
26 | 430 175 920 | LF | 80 | PIPE CULVERT, OPTIONAL MATERIAL, ELLIP/ARCH, 73"x97" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
27 | 430 518 100 | EA | 1 | STRAIGHT CONCRETE ENDWALLS, 18", SINGLE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
28 | 430 572 100 | EA | 1 | STRAIGHT CONCRETE ENDWALLS, 72", SINGLE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
29 | 430 982 125 | EA | 20 | MITERED END SECTION, OPTIONAL ROUND, 18" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
30 | 430 982 129 | EA | 9 | MITERED END SECTION, OPTIONAL ROUND, 24" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
31 | 430 982 625 | EA | 80 | MITERED END SECTION, OPTIONAL MATERIAL, ELLIP/ARCH, 14"x23" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
32 | 430 982 629 | EA | 10 | MITERED END SECTION, OPTIONAL MATERIAL, ELLIP/ARCH, 19"x30" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
33 | 0522 2 | SY | 217 | CONCRETE SIDEWALK AND DRIVEWAYS, 6" THICK |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
34 | 0527 2 | SF | 56 | DETECTABLE WARNINGS |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
35 | 0530 3 4 | SF | 61 | RIPRAP, RUBBLE, F&I, DITCH LINING |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
36 | 0570 1 2 | SY | 100356 | PERFORMANCE TURF, SOD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
Subtotal Roadway (Items 1 - 36) |  |  |  |  | 0
SIGNING AND PAVEMENT MARKINGS
37 | 0654 2 21 | AS | 2 | MIDBLOCK CROSSWALK: RECTANGULAR RAPID FLASHING BEACON, FURNISH & INSTALL- SOLAR, COMPLETE SIGN ASSEMBLY- SINGLE DIRECTION |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
38 | 0700 1 111 | EA | 60 | SINGLE POST SIGN, F&I GROUND MOUNT, UP TO 12 SF |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
39 | 0700 1 112 | EA | 1 | SINGLE POST SIGN, F&I GROUND MOUNT, UP TO 12-20 SF |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
40 | 0700 1 50 | AS | 2 | SINGLE POST SIGN, REMOVE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
41 | 0700 1 60 | AS | 42 | SINGLE POST SIGN, REMOVE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
42 | 0706 1 3 | EA | 1400 | RAISED PAVT MARKER, TYPE B |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
43 | 0710 11101 | GM | 7.392 | PAINTED PAVT MARKINGS, STANDARD, WHITE, SOLID, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
44 | 0710 11123 | LF | 500 | PAINTED PAVT MARKINGS, STANDARD, WHITE, SOLID, CROSSWALK, 12" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
45 | 0710 11125 | LF | 560 | PAINTED PAVT MARKINGS, STANDARD, WHITE, SOLID, STOP LINE, CROSSWALK, 24" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
46 | 0710 11160 | EA | 4 | PAINTED PAVT MARKINGS, STANDARD, WHITE, MESSAGE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
47 | 0710 11170 | EA | 40 | PAINTED PAVT MARKINGS, STANDARD, WHITE, ARROWS |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
48 | 0710 11201 | GM | 7.669 | PAINTED PAVT MARKINGS, STANDARD, YELLOW, SOLID, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
49 | 0710 11224 | LF | 750 | PAINTED PAVT MARKINGS, STANDARD, YELLOW, SOLID, DIAGONAL CHEVRON, 18" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
50 | 0710 11231 | GM | 0.773 | PAINTED PAVT, STANDARD-OTHER SURFACES, YELLOW SOLID, 10-30 SKIP, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
51 | 0711 11123 | LF | 500 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 12", CROSSWALK |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
52 | 0711 11125 | LF | 560 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 24", STOP LINE, CROSSWALK |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
53 | 0711 11160 | EA | 4 | THERMOPLASTIC, STANDARD, WHITE, MESSAGE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
54 | 0711 11170 | EA | 40 | THERMOPLASTIC, STANDARD, WHITE, ARROW |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
55 | 0711 11224 | LF | 750 | THERMOPLASTIC, STANDARD, YELLOW, SOLID, 18", DIAGONAL CHEVRON |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
56 | 0711 16101 | GM | 7.392 | THERMOPLASTIC, STANDARD-OTHER SURFACES, WHITE, SOLID, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
57 | 0711 16201 | GM | 7.669 | THERMOPLASTIC, STANDARD-OTHER SURFACES, YELLOW, SOLID, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
58 | 0711 16231 | GM | 0.773 | THERMOPLASTIC, STANDARD-OTHER SURFACES, YELLOW SOLID, 10-30 SKIP, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
Subtotal Signing and Pavement Markings (Items 37 - 58) |  |  |  |  | 0
UTILITY PLANS (WATER & SEWER)
59 | 0425 6 | LF | 27 | VALVE BOXES, ADJUST |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
60 | 1050 15001 | LF | 160 | UTILITY PIPE, ADJUST/MODIFY, 1.5" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
61 | 1050 15004 | LF | 40 | UTILITY PIPE, ADJUST/MODIFY, 4" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
62 | 1050 15008 | LF | 480 | UTILITY PIPE, ADJUST/MODIFY, 8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
63 | 1050 16002 | LF | 200 | UTILITY PIPE, REMOVE & DISPOSE, 2-4.9" (CONTINGENCY) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
64 | 1050 16003 | LF | 200 | UTILITY PIPE, REMOVE & DISPOSE, 5-8.0" (CONTINGENCY) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
65 | 1050 18001 | LF | 160 | UTILITY PIPE, PLUG & PLACE OUT OF SERVICE, 0-1.9" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
66 | 1050 18002 | LF | 66 | UTILITY PIPE, PLUG & PLACE OUT OF SERVICE, 2-4.9" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
67 | 1050 18003 | LF | 206 | UTILITY PIPE, PLUG & PLACE OUT OF SERVICE, 5-7.9" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
68 | 1050 18004 | LF | 20250 | UTILITY PIPE, PLUG & PLACE OUT OF SERVICE, 8-19.9" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
69 | 1050 42201 | LF | 730 | UTILITY PIPE- HDPE, F & I, WATER SERVICE LINE. 1" (18 CONNECTIONS) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
70 | 1050 42202 | LF | 300 | UTILITY PIPE- HDPE, F & I, WATER/SEWER, 2" (DISTRIBUTION LINE) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
71 | 1050 42204 | LF | 26 | UTILITY PIPE- HDPE, F & I, WATER/SEWER, 4" (DISTRIBUTION LINE) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
72 | 1050 42212 | LF | 734 | UTILITY PIPE- HDPE, F & I, WATER/SEWER, 6" (DISTRIBUTION LINE) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
73 | 1050 42216 | LF | 534 | UTILITY PIPE- HDPE, F & I, WATER/SEWER, 8" (DISTRIBUTION LINE) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
74 | 1050 42212 | LF | 19516 | UTILITY PIPE- HIGH DENSITY P.E., F & I, WATER MAIN, 12" (MAIN LINE) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
75 | 1050 42224 * | LF | 160 | HDPE CASING, DIRECTIONAL DRILL, F & I, WATER, 24" (MAIN LINE) * |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
76 | 1050 42202 | LF | 322 | UTILITY PIPE- HIGH DENSITY P.E, F & I, CASING, 2" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
77 | 1050 42204 | LF | 110 | UTILITY PIPE- HIGH DENSITY P.E, F & I, CASING, 4" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
78 | 1050 42212 | LF | 534 | UTILITY PIPE- HIGH DENSITY P.E., F & I, CASING, 12" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
79 | 1050 42216 | LF | 198 | UTILITY PIPE- HIGH DENSITY P.E., F & I, CASING, 16" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
80 | 1050 42224 | LF | 554 | UTILITY PIPE- HIGH DENSITY P.E., F & I, CASING, 24" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
81 | 1050 51208 | LF | 40 | UTILITY PIPE, DUCTILE IRON, F & I, SEWER, 8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
82 | 1055 51108 | EA | 10 | UTILITY FITTINGS, DUCTILE IRON, F & I, ELBOW, 8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
83 | 1055 51112 | EA | 31 | UTILITY FITTINGS, DUCTILE IRON, F & I, ELBOW, 12" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
84 | 1055 51208-6 | EA | 3 | UTILITY FITTINGS, DUCTILE IRON, F & I, TEE, 8"x6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
85 | 1055 51212-4 | EA | 1 | UTILITY FITTINGS, DUCTILE IRON, F & I, TEE, 12x4" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
86 | 1055 51212-6 | EA | 22 | UTILITY FITTINGS, DUCTILE IRON, F & I, TEE, 12"x6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
87 | 1055 51212-8 | EA | 10 | UTILITY FITTINGS, DUCTILE IRON, F & I, TEE, 12"x8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
88 | 1055 51310 | EA | 1 | UTILITY FITTINGS, DUCTILE IRON, F & I, TEE, 12"x12" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
89 | 1055 51312 | EA | 2 | UTILITY FITTINGS, DUCTILE IRON, F & I, REDUCER, 12"x8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
90 | 1055 51404 | EA | 1 | UTILITY FITTINGS, DUCTILE IRON, F & I, UNION, 4" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
91 | 1055 51406 | EA | 4 | UTILITY FITTINGS, DUCTILE IRON, F & I, UNION, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
92 | 1055 51408 | EA | 7 | UTILITY FITTINGS, DUCTILE IRON, F & I, UNION, 8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
93 | 1055 51508 | EA | 6 | UTILITY FITTINGS, DUCTILE IRON, F & I, CAP/PLUG, 8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
94 | 1055 51812 | EA | 1 | UTILITY FITTINGS, DUCTILE IRON, F & I, CROSS, 12"x8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
95 | 1080 21101 | EA | 11 | UTILITY FIXTURE, VALVE/METER BOX, FURNISH & INSTALL, 1" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
96 | 1080 21102 | EA | 5 | UTILITY FIXTURE, VALVE/METER BOX, FURNISH & INSTALL, 2" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
97 | 1080 23108 | EA | 3 | UTILITY FIXTURE- TAPPING SADDLE/SLEEVE, F & I, 8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
98 | 1080 24104 | EA | 1 | UTILITY FIXTURE, WATER GATE VALVE ASSEMBLY, F & I, 4" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
99 | 1080 24106 | EA | 45 | UTILITY FIXTURE, WATER GATE VALVE ASSEMBLY, F & I, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
100 | 1080 24108 | EA | 14 | UTILITY FIXTURE, WATER GATE VALVE ASSEMBLY, F & I, 8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
101 | 1080 24112 | EA | 60 | UTILITY FIXTURE, WATER GATE VALVE ASSEMBLY, F & I, 12" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
102 | 1080 25102 | EA | 1 | UTILITY FIXTURE- BLOWOFF ASSEMBLY, F & I, 2" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
103 | 1080 26102 | EA | 14 | UTILITY FIXTURE, VAC/AIR ASSEMBLY, FURNISH & INSTALL 2" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
104 | 1080 32102 | EA | 16 | UTILITY FIXTURE- SAMPLE POINT, F & I, 2" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
105 | 1080 33106 | EA | 3 | UTILITY FIXTURE, SEWER PLUG VALVE, F & I, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
106 | 1080 33108 | EA | 4 | UTILITY FIXTURE, SEWER PLUG VALVE, F & I, 8" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
107 | 1644113 08-FA | EA | 23 | FIRE HYDRANT, F&I, STD, 2" HOSE, 6" (FULL ASSEMBLY) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
108 | 1644113 08-SL | EA | 18 | FIRE HYDRANT, F&I, STD, 2" HOSE, 6" (STUB LINE & VALVE) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
109 | 1644900 | EA | 5 | FIRE HYDRANT, REMOVE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
Subtotal Utility Plans (Water & Sewer) (Items 59 - 109) |  |  |  |  | 0
LIGHTING
110 | 630-2-11 | LF | 18936 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
111 | 630-2-12 | LF | 2671 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
112 | 635-2-11 | EA | 245 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
113 | 639-1-122 | AS | 4 | ELECTRICAL POWER SERVICE, F&I, UNDERGROUND, METER PURCHASED BY CONTRACTOR |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
114 | 641-2-12 | EA | 8 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE POLE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
115 | 715-1-13 | LF | 24859 | LIGHTING CONDUCTORS, F&I, INSULATED, NO 4 TO NO 2 |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
116 | 715-7-11 | EA | 5 | LOAD CENTER, F&I, SECONDARY VOLTAGE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
117 | 715-7-11-2 | EA | 1 | LOAD CENTER, FURNISH ONLY, SECONDARY VOLTAGE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
118 | 715-65-266 | EA | 216 | LIGHT POLE COMPLETE, F&I, UTILITY CONFLICT POLE STANDARD FOUNDATION, 35' MOUNTING HEIGHT, 16' ARM LENGTH |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
119 | 715-65-266-2 | EA | 5 | LIGHT POLE COMPLETE, FURNISH ONLY, UTILITY CONFLICT POLE STANDARD FOUNDATION, 35' MOUNTING HEIGHT, 16' ARM LENGTH |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
120 | 715-500-1 | EA | 216 | POLE CABLE DISTRIBUTION SYSTEM, FURNISH AND INSTALL, CONVENTIONAL |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
121 | 715-500-1-2 | EA | 5 | POLE CABLE DISTRIBUTION SYSTEM, FURNISH ONLY |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
Subtotal Lighting (Items 110 - 121) |  |  |  |  | 0
COMMUNICATIONS
122 | STOF-1 | LF | 18130 | FURNISH & INSTALL VIA TRENCH METHOD (2) 4" CONDUITS EA W (4) 1" HDPE INNER DUCT EA W MULETAPE - (1) 4" W TRACER WIRE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
123 | STOF-2 | LF | 3211 | FURNISH & INSTALL VIA DIRECTIONAL BORE METHOD (2) 4" CONDUITS EA W (4) 1" HDPE INNER DUCT EA W MULETAPE - (1) 4" W TRACER |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
124 | STOF-3 | EA | 72 | FURNISH & INSTALL 30X48X36 HANDHOLES |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
125 | STOF-4 | LOC | 36 | INSTALL CONCRETE APRONS AROUND EACH PAIR OF HANDHOLES |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
126 | STOF-5 | SY | 200 | SIDEWALK RESTORATION (IF NEEDED) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
Subtotal Communications (Items 122 - 126) |  |  |  |  | 0
BASE BID (Items 1 - 126) |  |  |  |  | 0
ALLOWANCES
127 | A-1 | AL | 1 | Allowance (at direction of OWNER) - Unforeseen Conditions |  | 500000
Five Hundred Thousand Dollars and Zero cents
128 | A-2 | AL | 1 | Allowance (at direction of OWNER) - Glades Electric - For payments of all fees from Glades Electric for the electrical provisions |  | 300000
Three Hundred Thousand Dollars and Zero cents
129 | A-3 | AL | 1 | Allowance (at direction of OWNER) - Pole Banners |  | 20000
Twenty Thousand Dollars and Zero cents
130 | A-4 | AL | 1 | Allowance (at direction of OWNER) - Stub Outs - Additional WM and FM stub outs installation as needed to accommodate future development along West Boundary Road |  | 300000
Three Hundred Thousand Dollars and Zero cents
Subtotal Allowances (Items 127 - 130) |  |  |  |  | 1120000
TOTAL BASE BID AND ALLOWANCES (ITEMS 1 through 130) | [5 empty] | 1120000
Dollars and ____/100 cents
TOTAL BASE BID AND ALLOWANCES WRITTEN*
*AMOUNTS SHALL BE SHOWN IN BOTH WORDS AND FIGURES. IN CASE OF DISCREPANCIES, THE AMOUNT SHOWN IN WORDS SHALL GOVERN FOR EACH BID ITEM AND TOTAL BASE BID.
ALTERNATES
131 | ALT-1 | ALT | 1 | Museum Sidewalk |  | 0
Dollars and ____/100 cents (Write out total)
132 | ALT-2 | ALT | 1 | Fiber Installation |  | 0
Dollars and ____/100 cents (Write out total)
133 | ALT-3 | ALT | 1 | Field Office |  | 0
Dollars and ____/100 cents (Write out total)
134 | ALT-4 | ALT | 1 | West End Paving Section |  | 0
Dollars and ____/100 cents (Write out total)
Subtotal Alternates (Items 131 - 134) |  |  |  |  | 0
TOTAL BASE BID INCLUDING ALLOWANCES AND ALTERNATES (ITEMS 1 through ALT-4) | [5 empty] | 1120000
Dollars and ____/100 cents
TOTAL BASE BID INCLUDING ALLOWANCES AND ALTERNATES WRITTEN*
*AMOUNTS SHALL BE SHOWN IN BOTH WORDS AND FIGURES. IN CASE OF DISCREPANCIES, THE AMOUNT SHOWN IN WORDS SHALL GOVERN FOR EACH BID ITEM AND TOTAL BASE BID.
The bidder understands and agrees that the above Total Amount is inclusive of all work materials necessary to complete the Project as described in the Contract Documents.
CONTINUED ON NEXT PAGE
The STOF reserves the right to award or reject any or all bids.
AWARD OF CONTRACT AND TIME OF COMPLETION
The contract, if awarded, shall be to the most responsible bidder whose bid conforming to the specifications is the most advantageous to the STOF, considering prices bid, the experience, the qualifications of the bidder, and the bidders current and immediately available resources. Bid must comply with the requirements necessary to render it formal.
The WORK will be substantially complete within Six Hundred (600) calendar days from the commencement date stated in the Notice to Proceed. The WORK will be entirely complete (final) within Six Hudnred Fifty (650) calendar days from the commencement date stated in the Notice to Proceed. The specified calendar durations encompass all construction activities related to the WORK as outlined in Exhibit A1 - Alternate ALT-1 Museum Sidewalk and Exhibit A2 - Alternate ALT-2 West End Paving Section.
Liquidated damages will be applicable at Two Thousand Dollars and Zero Cents ($2,000.00) per day for each day beyond the Contract Time for Substantial Completion. The same rate of liquidated damages shall also be applied for each day of delay in achieving the contract time for Final Completion.
PROPOSAL SUMMARY
|  |  |  | Base Bid | 0
|  |  |  | Allowances | 1120000
|  |  |  | Alternate ALT-1 - Museum Sidewalk (see Alternate ALT-1) | 0
|  |  |  | Alternate ALT-2 - Fiber Installation (see Alternate ALT-2) | 0
|  |  |  | Alternate ALT-3 - Field Office | 0
|  |  |  | Alternate ALT-4 - West End Paving Section (see Alternate ALT-4) | 0
BY:
Print Name
Signature:
Title:
Company:
Email:
Dated this ________ day of ______________________, 20__.

## Alternate 1
RFP 37-2025 - West Boundary Road Construction (Big Cypress) (No. 384023) Exhibit A - Proposal Form REV001 (ALT 1)
The work to be performed under this Contract shall consist of furnishing all personnel, tools, equipment, materials, supplies, and manufactured articles for furnishing all transportation and services, including fuel, power water and essential communications, and for the performance of all labor, work, or other operations required for the fulfillment of the Contract in strict accordance with the Contract Documents.
Item No. | FDOT Pay Item | Unit | Est. Qty. | Description | Unit Price | Total Cost
ROADWAY
1 | 102 1 | LS | 1 | Maintenance of Traffic |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
2 | 104 10 3 | LF | 300 | Sediment Barrier |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
3 | 104 18 | EA | 1 | INLET PROTECTION SYSTEM |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
4 | 110 4 10 | SY | 25 | REMOVAL OF EXISTING CONCRETE (at Cowbone Culvert Crossing) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
5 | 120 1 | CY | 20 | REGULAR EXCAVATION |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
6 | 120 6 | CY | 20 | EMBANKMENT |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
7 | 520 1 10 | LF | 50 | CONCRETE CURB & GUTTER, TYPE F |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
8 | 520 2 4 | LF | 40 | CONCRETE CURB, TYPE D |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
9 | 522 1 | SY | 130 | CONCRETE SIDEWALK, 4" THICK |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
10 | 0527 2 | SF | 64 | DETECTABLE WARNINGS |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
11 | 0570 1 2 | SY | 200 | PERFORMANCE TURF, SOD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
SIGNING AND PAVEMENT MARKINGS
12 | 654 2 21 | AS | 6 | MIDBLOCK CROSSWALK: RECTANGULAR RAPID FLASHING BEACON, FURNISH & INSTALL- SOLAR, COMPLETE SIGN ASSY- SINGLE DIRECTION |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
13 | 700 1 11 | AS | 11 | SINGLE POST SIGN, F&I GROUND MOUNT, UP TO 12 SF |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
14 | 700 1 60 | AS | 5 | SINGLE POST SIGN, REMOVE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
15 | 700 1 50 | AS | 2 | SINGLE POST SIGN, RELOCATE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
16 | 706 1 3 | AS | 1 | MULTI-POST SIGN, RELOCATE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
17 | 425 1529 | EA | 10 | RAISED PAVEMENT MARKER, TYPE B |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
18 | 711 11 123 | LF | 105 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 12", CROSSWALK |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
19 | 711 11 125 | LF | 200 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 24", STOP LINE, CROSSWALK |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
20 | 711 11 160 | EA | 16 | THERMOPLASTIC, STANDARD, WHITE, MESSAGE |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
21 | 711 161 01 | LF | 200 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
TOTAL ALTERNATE ALT-1 (ITEMS 1 through 21) | [5 empty] | 0
Dollars and ____/100 cents
TOTAL ALTERNATE 1 ALT-1 WRITTEN*
*AMOUNTS SHALL BE SHOWN IN BOTH WORDS AND FIGURES. IN CASE OF DISCREPANCIES, THE AMOUNT SHOWN IN WORDS SHALL GOVERN FOR EACH BID ITEM AND TOTAL BASE BID.
BY:
Print Name
Signature:
Title:
Company:
Email:
Dated this ________ day of ______________________, 20__.

## Alternate 2
RFP 37-2025 - West Boundary Road Construction (Big Cypress) (No. 384023) Exhibit A - Proposal Form REV001 (ALT 2)
The work to be performed under this Contract shall consist of furnishing all personnel, tools, equipment, materials, supplies, and manufactured articles for furnishing all transportation and services, including fuel, power water and essential communications, and for the performance of all labor, work, or other operations required for the fulfillment of the Contract in strict accordance with the Contract Documents.
Item No. | FDOT Pay Item | Unit | Est. Qty. | Description | Unit Price | Total Cost
ROADWAY
1 | STOF-A2-1 | LS | 1 | Maintenance of Traffic |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
2 | STOF-A2-2 | LF | 26741 | CABLE PLACEMENT - 288F WITH 150' SLACK LOOPS IN EACH HH LOCATION |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
3 | STOF-A2-3 | LF | 26741 | 288 COUNT FIBER OPTIC CABLE - MATERIAL |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
4 | STOF-A2-4 | LF | 4290 | CABLE PLACEMENT - 48F FOR LATERALS |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
5 | STOF-A2-5 | LF | 4290 | 48 COUNT FIBER OPTIC CABLE - MATERIAL |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
6 | STOF-A2-6 | EA | 12 | SPLICE CASES & TRAYS - MATERIAL |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
7 | STOF-A2-7 | EA | 1 | INSTALL SPLICE CASE WITH FIBERS EXPRESSED IN TRAY (STA 210+20) |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
8 | STOF-A2-8 | EA | 11 | PREP 288F, PREP 48F AND INSTALL SPLICE CASE AT LATERALS - FIBERS EXPRESSED BUT NOT SPLICED |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
9 | STOF-A2-9 | LF | 1 | TESTING OF 288F AND 48F LATERALS - BIDIRECTIONAL VIA OTDR ONLY |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
10 | STOF-A2-10 | EA | 576 | SPLICE FIBERS |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
TOTAL ALTERNATE ALT-2 (ITEMS 1 through 10) | [5 empty] | 0
Dollars and ____/100 cents
TOTAL ALTERNATE 2 ALT-2 WRITTEN*
*AMOUNTS SHALL BE SHOWN IN BOTH WORDS AND FIGURES. IN CASE OF DISCREPANCIES, THE AMOUNT SHOWN IN WORDS SHALL GOVERN FOR EACH BID ITEM AND TOTAL BASE BID.
BY:
Print Name
Signature:
Title:
Company:
Email:
Dated this ________ day of ______________________, 20__.

## Alternate 4
RFP 37-2025 - West Boundary Road Construction (Big Cypress) (No. 384023) Exhibit A - Proposal Form REV001 (ALT 4)
The work to be performed under this Contract shall consist of furnishing all personnel, tools, equipment, materials, supplies, and manufactured articles for furnishing all transportation and services, including fuel, power water and essential communications, and for the performance of all labor, work, or other operations required for the fulfillment of the Contract in strict accordance with the Contract Documents.
Item No. | FDOT Pay Item | Unit | Est. Qty. | Description | Unit Price | Total Cost
ROADWAY
1 | 102 1 | LS | 1 | Maintenance of Traffic |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
2 | 104 10 3 | LF | 18520 | Sediment Barrier |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
3 | 110 1 1 | AC | 10.6 | Clearing & Grubbing |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
4 | 120 1 | CY | 4000 | REGULAR EXCAVATION |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
5 | 120 6 | CY | 1000 | EMBANKMENT |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
6 | 160 4 | SY | 17000 | TYPE "B" STABILIZATION |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
7 | 210 1 1 | SY | 22700 | REWORKING EXIST. SURFACE BASE MATERIAL |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
8 | 327 70 4 | SY | 7000 | MILLING EXISTING ASPHALT PAVEMENT, 3.0" AVG DEPTH |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
9 | 334 1 53 | TN | 1900 | SUPERPAVE SP-12.5 ASPHALT CONCRETE, TRAFFIC C, PG76-22 (1.5") |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
10 | 337 7 82 | TN | 1900 | ASPHALT CONC FRICTION COURSE, TRAFFIC C, FC-9.5, PG 76-22 (1.5") |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
11 | 430 175 148 | LF | 64 | PIPE CULVERT, OPTIONAL MATERIAL, ROUND, 48" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
12 | 430 982 141 | EA | 2 | MITERED END SECTION, OPTIONAL ROUND, 48" S/CD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
13 | 0570 1 2 | SY | 29000 | PERFORMANCE TURF, SOD |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
SIGNING AND PAVEMENT MARKINGS
14 | 700 1 11 | AS | 10 | SINGLE POST SIGN, F&I GROUND MOUNT, UP TO 12 SF |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
15 | 706 1 3 | EA | 500 | RAISED PAVEMENT MARKER, TYPE B |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
16 | 0710 11101 | GM | 3.5 | PAINTED PAVT MARKINGS, STANDARD, WHITE, SOLID, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
17 | 0710 11201 | GM | 3.5 | PAINTED PAVT MARKINGS, STANDARD, YELLOW, SOLID, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
18 | 0711 16101 | GM | 3.5 | THERMOPLASTIC, STANDARD-OTHER SURFACES, WHITE, SOLID, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
19 | 0711 16201 | GM | 3.5 | THERMOPLASTIC, STANDARD-OTHER SURFACES, YELLOW, SOLID, 6" |  | 0
Dollars and ____/100 cents (Write out total cost of Item)
TOTAL ALTERNATE ALT-4 (ITEMS 1 through 19) | [5 empty] | 0
Dollars and ____/100 cents
TOTAL ALTERNATE 3 ALT-4 WRITTEN*
*AMOUNTS SHALL BE SHOWN IN BOTH WORDS AND FIGURES. IN CASE OF DISCREPANCIES, THE AMOUNT SHOWN IN WORDS SHALL GOVERN FOR EACH BID ITEM AND TOTAL BASE BID.
BY:
Print Name
Signature:
Title:
Company:
Email:
Dated this ________ day of ______________________, 20__.